## Issues_Log
9 | Task | Description | Assigned To | Time Estimate (days) | Priority | Status | Comments
1 | Add Selenium |  | khalid | 3
2 | refacto on capitalize breadcrumbs. Make a strategy out of it |  | khalid | 3
3 | finalize nav |  | khalid | 1
4 | js core factory tu use as ks-app |  | khalid | 3
5 | review all structures and seperate themes and specif layout |  | khalid | 2
6 | add ci tool probably travis |  | khalid | 2
7 | create git repo for export |  | khalid | 0.5
8 | prepare dependencies for bower |  | khalid | 2

## Iteration_1
| Iteration 1 | [5 empty] | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Completed Task Days John | Completed Task Days Sue | Completed Task Days Developer 3 | Completed Task Days Developer 4 | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Holidays |  | Today Is
| Start Date | 2015-02-12 | [5 empty] | 0 | 18 | 18.5 |  |  |  |  | 0 | 0 |  | New Years | 2010-01-03 | 2015-02-13
| End Date | 2015-02-19 |  |  |  |  | 2015-02-12 | 1 | 15 | 15.5 | 3 | 0 |  |  | 3 | 1 | 3 | Family Day | 2010-02-12
| # of Developers | 1 |  |  |  |  | 2015-02-13 | 2 | 12 | 15.5 | 0 | 0 |  |  | 3 | 2 | 1.5 | Good Friday | 2010-04-22
| Efficiency Factor | 3 |  |  |  |  | 2015-02-16 | 3 | 9 | 15.5 | 0 | 0 |  |  | 3 | 3 | 1 | Easter Monday | 2010-04-24
| Work Days Total | 6 |  |  |  |  | 2015-02-17 | 4 | 6 | 15.5 | 0 | 0 |  |  | 3 | 4 | 0.75 | Victoria Day | 2010-05-23
| Dev Days Total | 6 |  |  |  |  | 2015-02-18 | 5 | 3 | 15.5 | 0 | 0 |  |  | 3 | 5 | 0.6 | Canada Day | 2010-07-01
| # of Task Work Days | 18 |  |  |  |  | 2015-02-19 | 6 | 0 | 15.5 | 0 | 0 |  |  | 3 | 6 | 0.5 | Labour Day | 2010-09-05
| m - Ideal Task Days Left | -3 | [15 empty] | Natal Day | 2010-10-01
| b - Ideal Task Days Left | 18 | [15 empty] | Thanksgiving | 2010-10-10
| m - Dev Days Used | 1 | [15 empty] | Christmas | 2010-12-26
| b - Dev Days Used | 0 | [15 empty] | Boxing Day | 2010-12-27
Task Id | Title | Estimate | Status | Get Estimate | Get Title | Get Status
1 | Add Selenium | 3 | 0 | 3 | Add Selenium | 0
2 | refacto on capitalize breadcrumbs. Make a strategy out of it | 3 | 0 | 3 | refacto on capitalize breadcrumbs. Make a strategy out of it | 0
3 | finalize nav | 1 | 0 | 1 | finalize nav | 0
4 | js core factory tu use as ks-app | 3 | 0 | 3 | js core factory tu use as ks-app | 0
5 | review all structures and seperate themes and specif layout | 2 | 0 | 2 | review all structures and seperate themes and specif layout | 0
6 | add ci tool probably travis | 2 | 0 | 2 | add ci tool probably travis | 0
7 | create git repo for export | 0.5 | 0 | 0.5 | create git repo for export | 0
8 | prepare dependencies for bower | 2 | 0 | 2 | prepare dependencies for bower | 0
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
| Testing, create tag, build release | 2
| Total Tasks Assigned | 18.5
| Available Time - Assigned time | -0.5
Formulas:
Work Date = WORKDAY(C2,([Work Days]-1),W2:W100)
Note on A14: Add the task ID's below